## Detail
|  |  |  | 0 | [6 empty] | NETWORK DETAIL
Customer | City | Address | Location | Floor | Unit | Accessories | SN | Installation Date | Period | End Date | Mac Address | Hostname | IP | SUBNET | GATEWAY | DNS | BOTASUPAL
BAYER | Surabaya | Supply Center Crop Science - Jl. Rungkut Industri I/12 Surabaya 60292 | C301-Logistic Office | 1st Floor | IMC300F | RF IDEAS CARD READER 805R1AKU, Card Reader Bracket | 3923PB54212 |  | 60 |  | 58:38:79:9E:49:88 | WIDD000013 | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | RC-011-20-0000-472
BAYER | Surabaya |  | B201-Production Office | 1st Floor | IMC300F | RF IDEAS CARD READER 805R1AKU, Card Reader Bracket | 3923PA52143 |  | 60 |  | 58:38:79:9D:BF:CC | WIDD000014 | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | RC-011-20-0000-471
BAYER | Surabaya |  | A201-SGC Office | 1st Floor | IMC300F | RF IDEAS CARD READER 805R1AKU, Card Reader Bracket | 3923PB54373 |  | 60 |  | 58:38:79:9E:48:7F | WIDD000015 | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | RC-011-20-0000-467
BAYER | Surabaya |  | B201-QA Office | 2nd Floor | IMC300F | RF IDEAS CARD READER 805R1AKU, Card Reader Bracket | 3923PB54301 |  | 60 |  | 58:38:79:9E:49:C4 | WIDD000016 | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | RC-011-20-0000-470
BAYER | Surabaya |  | B201- Main Office | 2nd Floor | IMC3010 | Paper Feed Unit PB3320, (9P28629) RDR-805R1AKU-G3, (9P28693)) USB cables(mini-137cm and A-28.9cm, | 9153RB30329 |  | 60 |  | 58:38:79:9F:D8:49 | WIDD000017 | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | RC-011-20-0000-466
BAYER | Surabaya |  | C305-Engineering | 2nd Floor | IMC300F | RF IDEAS CARD READER 805R1AKU, Card Reader Bracket | 3923PB54248 |  | 60 |  | 58:38:79:9E:49:04 | WIDD000018 | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | RC-011-20-0000-468
BAYER | Tangerang | Supply Center Crop Science - Tangerang PT Monagro Kimia Jl. Industri Manis 4 No.11, RT.002/RW.007, Manis Jaya, Jatiuwung, Tangerang City, Banten | Main Office building | 2nd Floor | IMC3010 | Paper Feed Unit PB3320, (9P28629) RDR-805R1AKU-G3, (9P28693)) USB cables(mini-137cm and A-28.9cm, | 9153RB30333 | 2024-02-22 | 60 | 2029-02-22 | 58:38:79:9F:D7:51 | WIDD000020 | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | RC-011-20-0000-465
BAYER | Tangerang |  | Engineering & Packaging Office | 1st Floor | IMC300F | RF IDEAS CARD READER 805R1AKU, Card Reader Bracket | 3923PA52134 | 2024-02-22 | 60 | 2029-02-22 | 58:38:79:9D:BE:C7 | WIDD000021 | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | RC-011-20-0000-474
BAYER | Tangerang |  | QC Lab Office | 1st Floor | IMC300F | RF IDEAS CARD READER 805R1AKU, Card Reader Bracket | 3923PA52059 | 2024-02-22 | 60 | 2029-02-22 | 58:38:79:9D:C0:3B | WIDD000022 | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | RC-011-20-0000-473
0
CANCELLED
BAYER | Cimanggis |  | BD-22 Warehouse 3 | 1st Floor | P 502 | Hard Disk Drive Option Type P18 | 5383PB01299 |  |  |  | 58:38:79:9D:CB:63 | WIDD000023 | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP
BAYER | Cimanggis |  | BD-11 Production Building | 1st Floor | IMC300F | RF IDEAS CARD READER 805R1AKU, Card Reader Bracket | 3923PA52133 |  |  |  | 58:38:79:9D:BF:1C | WIDD000024 | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | RC-011-20-0000-475
BAYER | Surabaya |  | RK9-Office WH RK9 | 2nd Floor | IMC300F | RF IDEAS CARD READER 805R1AKU, Card Reader Bracket | 3923PA52095 |  |  |  | 58:38:79:96:21:58 | WIDD000019 | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | Auto Obtained DHCP | RC-011-20-0000-469

## Time Pelaksanaannya
[22 empty] | Teknisi | IT
Imam
|  |  |  | TIMELINE PROJECT | [18 empty] | Akbar
No | TAHAPAN PELAKSANAAN & KEBUTUHAN |  | Note | JANUARI | [14 empty] | FEB |  | PIC
|  |  |  | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
X | Persiapan Perlengkapan Peralatan Staging
| o | Kertas | request 1 rim ke bu Siti, Imam / Ronald mintain ke Bu Siti | [17 empty] | Imam / Ronald
| o | Lakban | bekas yang kemaren masih ada ga, harusnya banyak tuh | [17 empty] | Imam / Ronald
| o | Spidol Permanen | bekas yang kemaren masih ada ga, harusnya masih kalo blom dicemilin | [17 empty] | Imam / Ronald
| o | Cutter / Gunting | pake bekas kemaren | [17 empty] | Imam / Ronald
| o | Colokan Listrik | pake bekas kemaren, punya gw tu! | [17 empty] | Imam / Ronald
| o | kabel LAN panjang 3 pcs | kalo ga ada minta ke Rudhy | [17 empty] | Imam / Ronald
| o | Tape Cutter | pake bekas kemaren | [17 empty] | Imam / Ronald
1 | BAYER
| o | Request Botasupal (11 pcs) | Di Pak Eko tgl 18 dikasih imam | [17 empty] | Imam / Ronald
| o | Status Card Reader (11pcs) | Sudah di Gudang, akan dipastikan sun2 18/1/2024 | [17 empty] | Sun2
| o | Request Toner untuk Staging Mesin | Ari Request PPS 18/1/2024 1 set IMC300, 1 set IMC 3010 khusus bayer, 1 P 502 | [17 empty] | Ari
| o | Koordinasi dengan GED | Ari Crosscheck ke GED 18/01/2024 : jadwal dan estimasi biaya | [17 empty] | Ari
| o | Staging - Builbook - Repacking | Start tgl 19 | [17 empty] | Imam | bar: JANUARI 19; JANUARI 22 to JANUARI 23
| o | Start Pengiriman Mesin | Start 23 - max 26 sampai | [17 empty] | Bu Nuri | bar: JANUARI 23 to JANUARI 26
| o | Start Instalasi Oleh Teknisi | estimasi tgl 30 | [17 empty] | Gilang / Sun2 | bar: JANUARI 30 to JANUARI 31
2 | Henkel
| o | Request Botasupal (8 pcs) | Di Pak Eko tgl 18 dikasih imam | [17 empty] | Imam / Ronald
| o | Status Card Reader (8 pcs) | Sudah di Gudang, akan dipastikan sun2 18/1/2024 | [17 empty] | Sun2
| o | Request Toner untuk Staging Mesin | Ari Request PPS 18/1/2024 1 set IMC 3010 | [17 empty] | Ari
| o | Koordinasi dengan GED | Ari Crosscheck ke GED 18/01/2024 : jadwal dan estimasi biaya | [17 empty] | Ari
| o | Staging - Builbook - Repacking | Start tgl 23 | [17 empty] | Imam | bar: JANUARI 23 to JANUARI 25
| o | Start Pengiriman | Start 25 - max 29 sampai | [17 empty] | Bu Nuri | bar: JANUARI 25 to JANUARI 26; JANUARI 29
| o | Start Instalasi Oleh Teknisi | TBC | [17 empty] | Gilang / Sun2 | bar: JANUARI 29 to JANUARI 31
3 | CORTEVA
| o | Request Botasupal (1 pcs) | Di Pak Eko tgl 18 dikasih imam | [17 empty] | Imam / Ronald
| o | Request Toner untuk Staging Mesin | Ari Request PPS 18/1/2024 1 set IMC 3010 | [17 empty] | Ari
| o | Koordinasi dengan GED | Ari Crosscheck ke GED 18/01/2024 : jadwal dan estimasi biaya | [17 empty] | Ari
| o | Koordinasi Teknisi 3rd Party untuk instalasi Medan | Gilang / P HJ koordinasi untuk harga dan informasi SOW | [17 empty] | Gilang / P HJ
| o | Staging - Builbook - Repacking | Start tgl 25 | [17 empty] | Imam | bar: JANUARI 25 to JANUARI 26
| o | Start Pengiriman | Start 25 - max 29 sampai | [17 empty] | Bu Nuri | bar: JANUARI 26; JANUARI 29 to JANUARI 31
| o | Start Instalasi Oleh Teknisi | [18 empty] | Gilang / Sun2 | bar: JANUARI 31 to FEB 2
| ESTIMASI TOTAL BIAYA |  | 0

## Timeline Pengiriman (hidden)
ESTIMASI MESIN SAMPAI GUDANG
48 |  |  | 9450000 | 48 | 48 |  | 48 | OKTOBER | [18 empty] | NOVEMBER | [29 empty] | DESEMBER
Location Code | KODE | Teknisi | Estimasi | City | Entity | Existing | Machine Type | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
MESA | FED001 | 3rd party | 400000 | Medan | PTFEI (21132) | DC-IV 3065 CPS | IM 3000 | bar: NOVEMBER 21 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9
MESA | FED002 | 3rd party | 400000 | Medan | PTFEI (21132) | DC-IV 3065 CPS | IM 3000 | bar: NOVEMBER 21 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9
BTHA | FED003 | Samsul | 100000 | Batam | PTFEI (21132) | DC-IV 3065 ST | IM C3000 (ARDF) | bar: NOVEMBER 21 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9
BTHA | FED004 | Samsul | 100000 | Batam | PTFEI (21132) | DC-IV 3065 ST | IM 3000 | bar: NOVEMBER 21 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9
PLMA | FED005 | 3rd party | 400000 | Palembang | PTSI (21145) | DocuCentre-IV 2060 ST | IM 3000 | bar: NOVEMBER 21 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9
PKUA | FED006 | 3rd party | 850000 | Pekanbaru | PTSI (21145) | DocuCentre-IV 2060 ST | IM 3000 | bar: NOVEMBER 21 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9
BPNT8 | FED007 | 3rd party | 850000 | Balikpapan | PTFEI (21132) | DC-IV 3060 CPS | IM 3000 | bar: NOVEMBER 22 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9; DESEMBER 12
BPNT8 | FED008 | 3rd party | 850000 | Balikpapan | PTFEI (21132) | DC-IV 3060 CPS | IM 3000 | bar: NOVEMBER 22 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9; DESEMBER 12
UPGA | FED009 | Gait | 100000 | Makassar | PTSI (21145) | DocuCentre-IV 2060 ST | IM 3000 | bar: NOVEMBER 22 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9; DESEMBER 12
MDCA | FED010 | 3rd party | 850000 | Manado | PTSI (21145) | DocuCentre-IV 2060 ST | IM 3000 | bar: NOVEMBER 22 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9; DESEMBER 12
BDJA | FED011 | 3rd party | 850000 | Banjarmasin | PTSI (21145) | DocuCentre-IV 2060 ST | IM 3000 | bar: NOVEMBER 22 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9; DESEMBER 12
DPST8 | FED012 | Djoko | 100000 | Bali | PTFEI (21132) | DC-IV 3065 ST | IM 3000 | bar: NOVEMBER 23 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9
DPST8 | FED013 | Djoko | 100000 | Bali | PTFEI (21132) | DC-IV 3060 CPS | IM 3000 | bar: NOVEMBER 23 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 9
SRGT8 | FED014 | Aris | 100000 | Semarang | PTSI (21145) | DC-IV 3060 CPS | IM 3000 | bar: NOVEMBER 24 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
SRGT8 | FED015 | Aris | 100000 | Semarang | PTSI (21145) | DC-IV 3060 CPS | IM 3000 | bar: NOVEMBER 24 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
SOCT8 | FED016 | Aris | 100000 | Surakarta | PTSI (21145) | DocuCentre-IV 2060 ST | IM 3000 | bar: NOVEMBER 24 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
JOGT8 | FED017 | Aris | 100000 | Yogyakarta | PTSI (21145) | DocuCentre-IV 2060 ST | IM 3000 | bar: NOVEMBER 24 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
SUBT8 | FED018 | Toni | 100000 | Sidoarjo | PTFEI (21132) | DC-IV 3060 CPS | IM 3000 | bar: NOVEMBER 24 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
SUBT8 | FED019 | Toni | 100000 | Sidoarjo | PTFEI (21132) | DC-IV 3060 CPS | IM 3000 | bar: NOVEMBER 24 to NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
FHQ | FED020 | Syaiful | 100000 | Jakarta | PTFEI (21132) | AP-IV C4430 ST | IM C3000 (ARDF) | bar: NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5
FHQ | FED021 | Syaiful | 100000 | Jakarta | PTFEI (21132) | DC-IV 5070 ST | IM 5000 | bar: NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5
FHQ | FED022 | Syaiful | 100000 | Jakarta | PTFEI (21132) | DC-IV 5070 ST | IM C3000 (ARDF) | bar: NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5
FHQ | FED023 | Syaiful | 100000 | Jakarta | PTFEI (21132) | DC-IV C5575 ST | IM C3000 (ARDF) | bar: NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5
FHQ | FED024 | Syaiful | 100000 | Jakarta | PTFEI (21132) | DC-IV C5575 ST | IM C3000 (ARDF) | bar: NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5
PPJA | FED025 | Angga | 100000 | Jakarta | PTSI (21145) | DocuCentre-IV 2060 ST | IM 3000 | bar: NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5
KWBA | FED026 | Nurhadi | 100000 | Jakarta | PTSI (21145) | DC-IV 3065 ST | IM 3000 | bar: NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5
PCBA | FED027 | Syaiful | 100000 | Jakarta | PTSI (21145) | DC-IV 3065 ST | IM 3000 | bar: NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5
FHQ | FED028 | Syaiful | 100000 | Jakarta | PTFEI (21132) |  | IM 3000 | bar: NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5
FHQ | FED029 | Syaiful | 100000 | Jakarta | PTFEI (21132) |  | IM C3000 (ARDF) | bar: NOVEMBER 25; NOVEMBER 28 to DESEMBER 2; DESEMBER 5
JKTT9 | FED030 | Putra | 100000 | Tangerang | PTFEI (21132) | DC-IV C5575 ST | IM C6000 (SPDF) | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
JKTT9 | FED031 | Putra | 100000 | Tangerang | PTFEI (21132) | AP-IV 5070 ST | IM 3000 | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
JKTT9 | FED032 | Putra | 100000 | Tangerang | PTFEI (21132) | AP-IV 5070 ST | IM 3000 | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
JKTT9 | FED033 | Putra | 100000 | Tangerang | PTFEI (21132) | AP-IV 5070 ST | IM 3000 | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
JKTT9 | FED034 | Putra | 100000 | Tangerang | PTFEI (21132) | AP-IV 5070 ST | IM 5000 | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
JKTT9 | FED035 | Putra | 100000 | Tangerang | PTFEI (21132) | DC-IV 5070 ST | IM 3000 | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
CGKIP | FED036 | Putra | 100000 | Tangerang | PTFEI (21132) | AP-IV 5070 ST | IM 5000 | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
JKTT9 | FED037 | Putra | 100000 | Tangerang | PTFEI (21132) | AP-IV C4430 ST | IM 5000 | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
PWLA | FED038 | Putra | 100000 | Tangerang | PTSI (21145) | DC-IV 3065 ST | IM 3000 | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
CGKIP | FED039 | Putra | 100000 | Tangerang | PTFEI (21132) | DocuCentre-V 4070 | IM C3000 (ARDF) | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
CGKIP | FED040 | Putra | 100000 | Tangerang | PTFEI (21132) |  | IM C3000 (ARDF) | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
CGKRT | FED041 | Putra | 100000 | Tangerang | FEC | DocuCentre-VI C3370 | IM C3000 (ARDF) | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
CGKIP | FED042 | Putra | 100000 | Tangerang | PTFEI (21132) | DocuCentre-V 4070 | IM 5000 | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
CGKIP | FED043 | Putra | 100000 | Tangerang | PTFEI (21132) | DocuCentre-V 4070 | IM 5000 | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
CGKIP | FED044 | Putra | 100000 | Tangerang | PTFEI (21132) | DocuCentre-V 4070 | IM 5000 | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
CGKIP | FED045 | Putra | 100000 | Tangerang | PTFEI (21132) | DocuCentre-VI C3370 | IM 5000 | bar: NOVEMBER 28 to DESEMBER 2; DESEMBER 5 to DESEMBER 6
TSYC | FED046 | Deri | 100000 | Cikarang | PTSI (21145) | DocuCentre-IV 2060 ST | IM 3000 | bar: NOVEMBER 30 to DESEMBER 2; DESEMBER 5 to DESEMBER 8
BDOT8 | FED047 | Yusuf | 100000 | Bandung | PTSI (21145) | DC-IV 3060 CPS | IM 3000 | bar: NOVEMBER 30 to DESEMBER 2; DESEMBER 5 to DESEMBER 8
BDOT8 | FED048 | Yusuf | 100000 | Bandung | PTSI (21145) | DC-IV 3065 ST | IM 3000 | bar: NOVEMBER 30 to DESEMBER 2; DESEMBER 5 to DESEMBER 8
9450000