## Indonesia
[8 empty] | Device Order Information |  |  |  | ACTION | Replacement Device Information | [7 empty] | Existing/Legacy Device Information | [9 empty] | Device Delivery Information | [5 empty] | Device Installation Status Information | [5 empty] | Disposal Information: DATA Wipe ¦ Removal
Country | Address | City | State | Zip | Building Name | Floor | Room | Ordered Labels/Sleeves/Badge Stickers/Print ID Cards and Posters | New Device Order Processed | Order Number | Order Line Number | IBM Proposal Keep/Refresh/Dispose | New Model Description | New Device Mfg Serial # | New Device MAC Address | New Device IP Address | New Device Hostname | New Subnet Mask | New Gateway Address | New Domain | Legacy Device Model | Legacy Device Mfg Serial # | Legacy Device IP Address | Legacy Device Equipment ID ¦ Hostname | Color/BW | Fax Number | Language | Legacy SubNet Mask | Legacy Gateway Address | Legacy Domain | RICOH Config Center | RICOH Config Email | New Device Delivery Scheduled YES ¦ NO | New Device Delivery Date | Truck Run | Delivery Status | New Device Install Date | New Device Install Complete YES ¦ NO | Install Success (1st Attempt) YES ¦ NO | Reason for Failure | Number of Driver/Tech Visits | Notes on failed 1st Install | Disposal Request Received YES/ NO | Data Wipe Date | Data Wipe Complete YES/NO | Device Pick Up Protocol Form Completed YES ¦ NO ¦ N/A | Legacy Device Removal Number | Legacy Device Pick Date | Legacy Device Pick Up Completed YES ¦ NO ¦ N/A | Software Compoment YES ¦ NO | Card Reader Installed YES/NO | Software Install Date | Software Install Complete YES ¦ NO
Indonesia | The Plaza Office Tower, 16 - 18th Floor | Jakarta | Other |  | The Plaza Office Tower | 17 | '- |  |  |  |  | Remove | [8 empty] | IM 430P | 3351P952217 | 9.187.183.16 | idjktvj4 | BW
Indonesia | The Plaza Office Tower, 16 - 18th Floor | Jakarta | Other |  | The Plaza Office Tower | 17 | 17.02 |  |  |  |  | Remove | [8 empty] | IM 430P | 3351P952317 | 9.187.183.11 | idjktvj2 | BW
Indonesia | The Plaza Office Tower, 16 - 18th Floor | Jakarta | Other |  | The Plaza Office Tower | 17 | Finance printer room |  |  |  |  | Remove | [8 empty] | IM 430P | 3351P952318 | 9.187.183.17 | idjktvj5 | BW
Indonesia | The Plaza Office Tower, 16 - 18th Floor | Jakarta | Other |  | The Plaza Office Tower | 17 | CGM office |  |  |  |  | Remove | [8 empty] | MP C407SPF | C498P400913 | 9.187.183.15 | idjktv7d | Color
Indonesia | The Plaza Office Tower, 16 - 18th Floor | Jakarta | Other |  | The Plaza Office Tower | 17 | '- |  |  |  |  | IM C4510 | IM C4510 | 9174R720539 | 58-38-79-A9-FA-EC | 9.187.183.13 | idjktvj6 | 255.255.255.0 | 9.187.183.1 | id.ibm.com | MP C4504 | G717M350523 | 9.187.183.24 | idjktv0a | Color